## Sheet1
Task | Duration | Start | Finish
Requirements Gathering & Analysis | 35d | 14/10/19 | 29/11/19
Collect user requirements | 5d | 14/10/19 | 18/10/19
Perform user requirements analysis | 20d | 21/10/19 | 15/11/19
User requirement signoff | 0 | 18/11/19 | 18/11/19
Prepare user stories and documentation | 10d | 18/11/19 | 29/11/19
System Analysis and Design | 37d | 2019-02-12 | 24/01/20
Perform system analysis | 15d | 2020-06-01 | 24/01/20
Prepare for program specifications | 10d | 2019-02-12 | 13/12/19
System Development | 12d | 14/02/20 | 2020-02-03
Perform program developments | 12d | 14/02/20 | 2020-02-03
Testing | 37d | 2020-02-03 | 24/04/20
System Test | 15d | 2020-02-03 | 20/03/20
Prepare for test plans | 5d | 2020-02-03 | 2020-06-03
Execute test plans | 10d | 2020-09-03 | 20/03/20
User Acceptance Test | 22d | 23/03/20 | 24/04/20
UAT environment preparation | 5d | 23/03/20 | 27/03/20
Perform UAT | 15d | 30/03/20 | 21/04/20
UAT signoff | 0 | 24/04/20 | 24/04/20
Deployment | 5d | 2020-01-05 | 2020-08-05
Production release preparation | 5d | 2020-01-05 | 2020-07-05
Go Live | 0 | 2020-08-05 | 2020-08-05